## T2 Publication List
Problem ID*+ | Originating Service | Issue Description (BOD) | Impacted Module | Expected PROD Delivery Date
Production Problems Impacting CLM
PBI000000229120 |  | Align the highlight effects and focusable state on the table module for mouse and keyboard usage between different browsers.á The keyboard navigation inside the table is using the default browser effects. The focus styling should be customized to have better visibility. | CLM | 2025-06-14
PBI000000229148 |  | When the user navigates back to the previously opened screen(s) via the browser button or the breadcrumb navigation, the previously shown information is not retrieved correctly and an empty result set is displayed. This behaviour occurs on the CLM GUI screens "List of Minimum Reserve (Direct)", "List of Minimum Reserve (Indirect)" and "List of Minimum Reserve (Pool)". | CLM | 2025-06-14
PBI000000229187 |  | The text shown in the field 'Subject' on the screen 'List of Broadcasts' is for some broadcasts incorrect regarding the spelling. This has to be corrected. Note: the business content of the field is correct, only the spelling is wrong. | CLM | 2025-06-14
PBI000000231059 |  | 1. Business Scenario Description: In case a camt.005 is sent with an 'Account Identification' referrencing a non-existing cash account (i.e. incorrect cash account identification is provided) the error E112 is expected but not raised (instead E118 is returned). 2. Issue Description: Software issue of VR01420. 3. Workaround: not necessary 4. TARGET Services concerned: RTGS 5. Effects and restrictions on concerned TARGET Service: Non 6. Required SW change: Yes. | CLM | 2025-06-14
PBI000000231211 |  | 1. Business Scenario Description: Sending a cash transfer order query (camt.005) which includes a reversed inter-service standing order liquidity transfer in it's answer (camt.006). 2. Issue Description: The credit- and debit cash accounts are interchanged in the camt.006 response related to this cash transfer. In case the target-settlement service was T2S or TIPS the transit account in CLM is referenced instead of the target cash account. 3. Workaround: not avai÷able 4. TARGET Services concerned: RTGS/CLM camt.006 delta query response 5. Effects and restrictions on concerned TARGET Service: The credit- and debit cash accounts are interchanged in the camt.006 response related to this cash transfer 6. Required SW change: Correct the interchanged debit and cash accounts in the camt.006 response | CLM | 2025-06-14
PBI000000231939 |  | 1. Business Scenario Description: When specifying a sorting by output parameter 'Business Case ID' in ascending order on the CLM/RTGS GUI screen 'Query Messages', the result list on the following list screen is not sorted correctly. 2. Issue Description: The sorting currently does not consider the complete numerical value of the field 'Business Case ID' and seems to consider only the first 3 digits of the business case ID. 3. Workaround: No 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: The result set can not be correctly sorted by the output parameter 'Business Case ID'. 6. Required SW change: Yes, adjust SQL-statement to enable correct sorting. | CLM | 2025-06-14
PBI000000233168 |  | 1. Business Scenario Description: A leading CLM account holder can request its 'Leader View' using the MRFQ camt.003. 2. Issue Description: Currently there is no way for a leading CLM accout holder which is also the co-manager of other leading CLM account holding parties (= co-managees) to only query its own 'Leader View'. 3. Workaround: A query without any further search criteria will provide all available leader views (i.e. of co-manager + co-managees), including the own leader view. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: see above. 6. Required SW change: Adjust the relevant validation rule to allow co-managers to query their own leader-view only using the 'AccountServicerBIC' as search criteria | CLM | 2025-06-14
PBI000000233170 |  | 1. Business Scenario Description: Payment messages send during end of day processing (CCML) but before close of service should be parked for the moment and processed after change of business day. 2. Issue Description: The inbound payments get parked but when sent between CCML and CCOS (i.e. before CCOS) receive the error message "E018 U2A action outside allowed acceptance time frame". Thus, even payments for future business days will be rejected once processing started again. 3. Workaround: Send message at different Business day Event (e.g. RTS) 4. TARGET Services concerned: T2 CLM/RTGS 5. Effects and restrictions on concerned TARGET Service: No 6. Required SW change: Yes, Backend processing has to be changed. | CLM | 2025-06-14
PBI000000233417 |  | 1. Business Scenario Description: Executing the A2A Cash Transfer Query with an equal amount search restriction. 2. Issue Description: The Query Response contains also Cash transfers which with a larger settlement amount than originally requested in the Query message. 3. Workaround: Apply a filter on "AmtWthCcy" field in camt.006 with "EQAmt" of camt.005 message. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Querying cash transfers with a specific amount will also contain cash transfers with a larger settlement amount. 6. Required SW change: Yes, correct the filter on backend site. | CLM | 2025-06-14
PBI000000233426 |  | 1. Business Scenario Description: During business day processing in T2 SO LTs are created and settled. In case the liquidity is not sufficient to settle the whole amount of the SO, a ProRataRate is calculated. 2. Issue Description: When calculating the final amount of the SO LT to be created and settled the ProRataRate is rounded down. Based on the available liquidity on the cash account this can lead to a 0.00 value, so small amounts of available liquidity are not correctly calculated. This issue only occurs in cases where the available liquidity is very low and the amount of the SO is very high (in this case 18 digits). 3. Workaround: Transfer the small amount per manual LT or reduce the amount of the SO to a value closer to a real live value. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: The small amount will not be transfered via SO LT and remains on the cash account. 6. Required SW change: Yes. Make sure to not round/truncate the ProRataRate, rather use the original value and only round the final amount to be settled. | CLM | 2025-06-14
PBI000000233504 |  | 1. Business Scenario Description: Connected payments (CONP) should only be possible to settle on MCAs which are also the default cash account of the account owner as a credit line is only allowed on such cash accounts. 2. Issue Description: Currently it's not validated whether the addressed MCA is a default cash account. Thus a connected payment could currenlty create a credit line on a non-default MCA. 3. Workaround: Do not use CONP for non-default MCAs. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Creation of credit line on non-default MCAs possible 6. Required SW change: Enhancement of VR00320 via SDD-CN | CLM | 2025-06-14
PBI000000233697 |  | 1. Business Scenario Description: An automated pull LT (LAUT) is created when a CBO is queued in CLM. The LAUT will be sent to RTGS requesting the necessary liquidity for the CBO settlement. This liquidity transfer can be queued in RTGS in case of insufficient liquidity on the RTGS DCA. Whenever the necessary liquidity changes in CLM it should sent a new autoamted pull LT with the updated liquidity to RTGS. 2. Issue Description: In case the queued CBO in question is rejected during the business day (e.g. due to configured reject time for this payment) no new updated automated pull LT will be sent to RTGS to inform RTGS that no more liquidity is needed. Thus the automated LT will still be queued on the RTGS DCA. 3. Workaround: Either not submit a CBO with a reject time or make sure that sufficient liquidity is either on the MCA or DCA. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: In this specific scenario (insufficient liquidity on the CLM MCA AND the related RTGS DCA and a queued CBO with a reject time) the automated LT in RTGS might stay queued even when no more liquidity is needed in CLM. 6. Required SW change: Update CLM rejection process to consider this scenario. | CLM | 2025-06-14
PBI000000234061 |  | 1. Business Scenario Description: A cash transfer query submitted with a cash account number (tag '.../AcctNtrySch/AcctId/EQ/Othr/Id) as search criteria should only return cash transfers debiting or crediting this cash account from the cash account perspective. 2. Issue Description: When the return criteria Debotr and Creditor ('...PmtRtrCrit/DbtrInd' and ''...PmtRtrCrit/CbtrInd') are both used the camt.006 may return a cash transfer twice (the debit and the credit perspective) instead of only the perspective of the queried cash account 3. Workaround: - 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Cash Transfer Query might return a cash transfer twice 6. Required SW change: Yes | CLM | 2025-06-14
PBI000000234111 |  | 1. Business Scenario Description: In the 4-eyes mode a user has the choice either to confirm a task, directly withdraw the task or edit a task. When a user wants to edit a task via the screen "Details of Task Queue" the initial task needs to be withdrawn first and a new task needs to be created. Therfore the GUI automatically withdraws this task first and afterwards a popup is automatically opened to edit the previous inputs and generate a new task. This bug emerges when a user edits a task with the task type "Administrate Minimum Reserve Penalty". 2. Issue Description: When confirming the initial withdrawal of the original task, the task is withdrawn correctly. The expected popup to create the new task is not displayed but ends with error message 400. 3. Workaround: Instead of editing the original task the user can withdraw the task and create a new task via the minimum reserve infringement screen. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: No. The user can still perform the process of administrating minimum reserve penalties and only the quality of life feature of a prefilled edit popup is affected. 6. Required SW change: Yes. Adapt backend code of the enpoint to handle the input id correctly and add a filtering for the minimum reserve period indicated by the input id. | CLM | 2025-06-14
PBI000000234322 |  | 1. Business Scenario Description: A payment which is not yet executed can be revoked by the customer. 2. Issue Description: A revocation of a payment submitted via U2A will result in the business transaction not being closed automatically (i.e. payment gets revoked correctly but business transaction does not close). This issue can be tested by the customer by looking at the GUI screen Query Business Cases. 3. Workaround: Close business transaction via LLI 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: LLI might be required. 6. Required SW change: Take revocation status in account when checking whether business transaction has to be updated. | CLM | 2025-06-14
PBI000000234329 |  | 1. Business Scenario Description: Viewing a Rejected Payment in Screen RTGS or CLM "List of Task Queue" and "Details of Task Queue" which was entered via U2A in RTGS/CLM GUI 2. Issue Description: No amount is shown in List of Task Queue and Details of Task Queue Screens This issue can be tested by the customer and is not currency-related. 3. Workaround: Use the Overview Task on the same screen below to view this information. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: none 6. Required SW change: Yes, backend access for List of Task Queue and Details of Task Queue Screens have to be updated. | CLM | 2025-06-14
PBI000000234418 |  | 1. Business Scenario Description: Being logged in to the CLM or RTGS GUI. 2. Issue Description: The broadcast icon is coloured in orange, which does suggest that there are new broadcasts, while there aren't any. This issue can be tested by the customer and is not currency-related. 3. Workaround: none 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: none 6. Required SW change: Yes, change the unread broadcast flag to the correct data type. | CLM | 2025-06-14
PBI000000234585 |  | 1. Business Scenario Description: Messages sent to T2 during Close of Service (CoS) are not processed immediately, rather they are parked. With the start of the next upcoming business day those messages are processed. 2. Issue Description: Due to INC000000430474 RCOS/CCOS was delayed later than the scheduled time of the start of the new business day. Due to this delay the parked messages were not successfully processed and were kept in parking status 3. Workaround: In case of a delay of RCOS/CCOS make sure to have a pit stop before CRTI and only force the pitstop once messages are not parked anymore. Possible solutions will be discussed in PBI000000234481 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Messages will be kept parked and not processed 6. Required SW change: Always wait for the messages in parked status to be unparked in order to make sure they can be processed | CLM | 2025-06-14
PBI000000234585 |  | 1. Business Scenario Description: E.g. entering "õ,÷,³" into any of the multi smart select switchable fields (for example the field "MCAs") of the account selection section of the "Query Dashboard Liquidity Overview" screen in the CLM GUI. 2. Issue Description: Validation is missing for all fields, allowing the input of incorrect characters. This issue can be tested by the customer and is not currency-related. 3. Workaround: 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: NA 6. Required SW change: Add the validation rules to the fields. | CLM | 2025-11-22
PBI000000235189 |  | 1. Business Scenario Description: In case an MCA has insufficient liquidity for the settlement of a CBO CLM tries to pull the necessary liquidity via automated liquidity transfer from the linked RTGS DCA if configured. In case the CBO is a warehoused payment where the execution date is reached, the automated LT will be created after the inital settlement attempt during even processing CRTI. 2. Issue Description: In case the start of the change of business day in RTGS is delayed it may happen that the revalidation of warehoused payments in CLM (event CRTI) is started before RTGS RSOD is executed. This will result in the rejection of the created automated liquidity transfers in case they reach RTGS before RSOD is processed. This issue can be tested by the customer and is not currency-related. 3. Workaround: Pull necessary liquidity manually or wait for another CBO to be queued (then the sum of the necessary liquidity will be pulled automatically). 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Liquidity may not be automatically pulled for queued (previously warehoused) payments. 6. Required SW change: Change processing of automated liquidity transfers in RTGS received before RSOD. | CLM | 2025-11-22
PBI000000235479 |  | 1. Business Scenario Description: As of CCML SoA is generated for every cash account that is configured in SoA configuration. The generated SoA is stored in T2 so it can be later retrieved. If push mode is set to TRUE for this configuration, the SoA will be sent to the PTA of the party opting for the SoA. In case a party has no routing/PTA the push flag is overwritte by T2 to FALSE. When all SoA are generated, CCML continues and CCOS follows immediately. 2. Issue Description: The party opting for the SoA in push mode has no party service link configured which is a data constellation not expected in T2 and therefore the check if the opting party has a valid routing/PTA did not work for the party. Due to this missing check CLM tried to send out the SoA although it should not. The error occured when trying to send out the SoA causes CCML to be stuck and business day does not continue. This issue can be tested by the customer and is not currency-related. 3. Workaround: Set push flag in CRDM to FALSE or update flag to FALSE in T2 by LLI 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: SoA for this account is not sent out and CCML is stuck. 6. Required SW change: Make sure to include parties w/o a party service link in the check if routing/PTA exists for this party. | CLM | 2025-06-14
Problem ID*+ | Originating Service | Issue Description (BOD) | Impacted Module | Expected PROD Delivery Date
Production Problems Impacting RTGS
PBI000000227838 |  | While the Algo 4 starts, all cash transfer orders of an AS batch in procedure B are switching to cash transfer status "Earmarked" before next settlement attempt. This happens at every Algo 4 start. The screen currently displays "Queued" cash transfer orders only and therefore, just before start of the Algo, the result list is empty. However, also the earmarked cash transfer orders of AS batches in procedure B must be taken into consideration as unsettled cash transfer orders in this screen. | RTGS | 2025-06-14
PBI000000228554 |  | In the CLM and RGTS GUI (Details of Message / Details of File screens), textarea-fields that show xml content are currently filled with a white background colour. This leads to the wrong impression that those fields can be edited. The fields should therefore be filled with grey background colour to indicate that no input is possible. | RTGS | 2025-06-14
PBI000000229013 |  | The context menu 'Display Cash Transfer' on the screen 'List of AS Batches' currently uses the 'AS Batch Message Reference' for the navigation to the screen 'List of Cash Transfers'. The same value for 'AS Batch Message Reference' might be used by different ancillary systems, so this navigaion criterion is not sufficient in order to exactly show the cash transfers of the relevant AS batch. To achieve uniqueness the Business Case ID has to be added as an additional navigation criterion. The implementation and the UHB have to be modified accordingly. In this context the description of the UHB regarding the context menus 'Details' and 'Display AS Batch Processing Log' will be corrected, as the current implementation (correctly) does not use the 'AS Batch Message Reference' for the navigation but an technical (internal) ID. This is an editorial issue. | RTGS | 2025-06-14
PBI000000229113 |  | Currently the "Increase" and "Decrease" queue position context menu for AS Transfers is shown the payment bank users even though only the related CB can change the queue position. With this fix the context menus "Increase" and "Decrease" will be removed for PB users. The execution of this action is already correctly prevented in this case and the GUI will now be aligned with this behaviour. | RTGS | 2025-06-14
PBI000000229918 |  | In the Current State of the software the Field "All Settlement Banks of AS" on the Screens "List of Broadcasts" and "Details of Broadcasts" in RTGS does show each individual Settlement Bank and instead of the addressed AS. With this Fix the behaviour is restored to the desired state and aligned with the Screen "New Broadcast" so that the field "All Settlement Banks of AS" contains the AS which Settlement Banks are addressed. | RTGS | 2025-06-14
PBI000000230174 |  | The customer sent an instruction with an unknown message type. Usually in this case an admi.007 should be created with error code E002. Due to the fact of an invalid BAH within the message the processing stopped and no admi.007 response was sent out to the customer. Hence he was not informed automatically about the invalid sent message. | RTGS | 2025-06-14
PBI000000230179 |  | When a customer queries his minimum reserve requirements (camt.003 fullfillment/requirement query) on the same day that he gets obliged for minimum reserve the query will abend with a technical error. This happens because the mandatory accumulated end of day minimum reserve balance from the previous business day does not exist. Consequently the customer does not get any response in this rare case. | RTGS | 2025-06-14
PBI000000231015 |  | 1. Business Scenario Description: In AS procedure B two 'high' priority payments were queued at the same time. The cash account (RTGS DCA) had no liquidity but a rule based liquidity transfer configured for high queued payments (linked MCA). Consequently as both of the payments were queued within a few ms the first payment created a LRQP camt.050 pull to CLM. While the rule based pull LT for the first payment succeeded the pull LT for the second queued payment failed. 2. Issue Description: Due to an implementation error the amount of the second pull LT is incorrectly set to NULL. 3. Workaround: not available 4. TARGET Services concerned: T2 RTGS high priority queued payments 5. Effects and restrictions on concerned TARGET Service: If two 'high' priority payments are queued at the same time (within few ms) and the RTGS DCA is lacking the necessary liquidity, the automated LT to provide the liquidity for the second 'high' priority payment fails. 6. Required SW change: Correct the implementation bug to correctly set the amount in the second automated LT according to the liquidity need | RTGS | 2025-06-14
PBI000000231058 |  | 1. Business Scenario Description: Sending camt.005 with elements a combination of the elements 'Account Owner', 'Account Identification', 'Account Servicer' gives an result instead of the expected Error code E111. These elements should be mutually exclusive. 2. Issue Description: Software issue as the defined validation rule does not work as intended. 3. Workaround: Do not combine those elsements 4. TARGET Services concerned: RTGS 5. Effects and restrictions on concerned TARGET Service: Non 6. Required SW change: Yes. | RTGS | 2025-06-14
PBI000000231269 |  | 1. Business Scenario Description: After sending a camt.021 a corresponding camt.004 is expected for the sending party 2. Issue Description: After starting a maintenance window on mondays no camt.004 corresponding to the incoming camt.021 is sent with the Start of RTGS RTS II 3. Workaround: No known workaround 4. TARGET Services concerned: T2 RTGS 5. Effects and restrictions on concerned TARGET Service: No outbound message is created, the customer will not be informed about balances of the referenced sub accounts of the AS 6. Required SW change: Correct the flow to send the corresponding Outbound messages | RTGS | 2025-06-14
PBI000000231860 |  | 1. Business Scenario Description: Viewing the "New Reservation Amount" Type Task in T2 U2A Screen "List of Task Queue" / "Details of Task Queue" 2. Issue Description: When Viewing the the "New Reservation Amount" Type Task in T2 U2A Screen "List of Task Queue" / "Details of Task Queue" the "Old Amount" is not correctly displayed. 3. Workaround: No 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: The old value of a Modified Reservation is not Displayed to the User 6. Required SW change: The Old value needs to be stored when creating the Task | RTGS | 2025-06-14
PBI000000232018 |  | 1. Business Scenario Description: A mulilateral limit modification which decreases the limit will be set to pending when the referenced cash account has insufficient liquidity. It will be retriggered when the cash account gets new liquidity. In case the task will still be pending due to still insufficient liquidity after the second execution attempt the task might get stuck due to this issue. 2. Issue Description: The execution of a such a task will fail due to a data inconsistency and the task might not be executed anymore afterwards. 3. Workaround: Sending a new limit modification will solve the issue. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: no 6. Required SW change: Yes | RTGS | 2025-06-14
PBI000000232164 |  | Business Scenario Description: When entering a liquidity transfer via the RTGS GUI screen ôNew Liquidity Transfer to Technical Account Procedure Dö the correct screen is not displayed in the divider ôOverview Taskö on the screen ôDetails of Task Queueö. Issue Description: The user doesnÆt see the specific information on the screen ôDetails of Task Queueö which could be needed to control the entered task as a second user, for example the Account Number of the Instructing Agent, the Account BIC of the Instructed Agent and the End to End ID. Workaround: No workaround for the missing information in the screen ôDetails of Task Queueö for the control of a second user is available. TARGET Services concerned: T2 (RTGS) Effects and restrictions on concerned TARGET Service: This implementation leads to diminished possibilities of a second user to control the entered liquidity transfer or to edit an existing task when the screen ôNew Liquidity Transfer to Technical Account Procedure Dö was used. Required SW change: A case distinction for the task type ôEnter Liquidity Transferö depending on used input screen has to be implemented. | RTGS | 2025-06-14
PBI000000231804 |  | 1. Business Scenario Description: The popup functionality RTGS Cash Account Reference Data û Query Screen for smart select boxes for a Party BIC or Party Name in several AS Query Screens will be changed to the popup RTGS Party Reference Data û Query Screen. This reduces the list of results displayed to the user significantly after searching with the popup functionality and leads to a consistent usage of the popup screen RTGS Party Reference Data û Query Screen for all smart select boxes for the search criteria Party BIC and Party Name. 2. Issue Description: Several RTGS AS screens offer the possibility to search for a Party BIC or Party Name using a popup search functionality. Currently this popup is linked to the Cash Account Reference Data û Query Screen. This leads û depending on the data scope of the user - to a wide range of results when the query is not restricted by using any search criteria as the listed results are based on all existing accounts. Using the Party Reference Data û Query Screen instead of the Cash Account Reference Data û Query Screen as a popup for a Party BIC or Party Name, will reduce the result set significantly. Moreover, the Party Reference Data û Query Screen is more eiligible when searching for a Party BIC or Party Name. 3. Workaround: Restriction of result list via the popup by setting of further search criteria 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: No restrictions 6. Required SW change: For several smart select boxes for a Party BIC or Party Name in AS Query screens, the popup screen for the search functionality should be changed from the RTGS Cash Account Reference Data - Query Screen to the RTGS Party Reference Data - Query Screen. The following screens are affected: - Query AS Batches [RTGS] - Query AS Procedures and Cycles [RTGS] - Query AS Liquidity Overview [RTGS] - Query Queued AS Transfer Orders by Batch [RTGS] - Query AS Batch Liquidity Summary for Guarantee Fund Mechanism [RTGS] - Query AS Batch Liquidity Summary by Settlement Bank [RTGS] The RTGS UHB, the specification of the screen templates and the implementation must be adapted accordingly. | RTGS | 2025-06-14
PBI000000232567 |  | 1. Business Scenario Description: When the business day is loaded in CLM/RTGS validations are in place to make sure events are scheduled well and can be processed. Maintenance windows events need to be present in CLM and RTGS at the same scheduled time. For all invalid events a tivoli alert is generated 2. Issue Description: In case of a rescheduling the update of the events changing from Invalid to Valid does not work in all cases and therefore the event stays invalid. 3. Workaround: Make sure event is set to valid 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: MW events are not successfully processed and business day is stuck. 6. Required SW change: Make sure to consider correct update to valid. | RTGS | 2025-06-14
PBI000000232074 |  | 1. Business Scenario Description: When using the context menu entry "Display Message" in the CLM/RTGS List/Details of Files screens the user is forwarded to the CLM/RTGS List/Details of Messages screen and the message(s) (sent with the file) are displayed. 2. Issue Description: After forwarding to the List/Details of messages screen no entries are found due to a wrong forwarding criterion and therefore, the messages of the file are not displayed to the user. 3. Workaround: All messages can be found via the Query Messages screen directly. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: see above 6. Required SW change: Introduce the unique forwarding criterion "(Technical) File ID" in both List/Details of Files and List/Details of Messages screens. A SDD-CN is required. | RTGS | 2025-11-22
PBI000000232978 |  | 1. Business Scenario Description: Querying and displaying rejected payments (pacs.004, pacs.008, pacs.009) on the RTGS GUI screens "List/Details of Task Queue". 2. Issue Description: For payments with the status "Rejected", for which no cash transfer order was created, the column "Amount" shows an empty value, even though an amount had previously been entered when creating the payment. 3. Workaround: No 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: For payments with the status "Rejected", the user can not identify the corresponding amount on the Task Queue screens. 6. Required SW change: Correct software behaviour so that the amount is always shown, independent of the status of the payment. | RTGS | 2025-06-14
PBI000000232997 |  | 1. Business Scenario Description: Using the breadcrumb navigation functionality after submitting a payment order via RTGS/CLM GUI screens "New Customer Credit Transfer", "New Financial Institution Credit Transfer" or "New Payment Return". 2. Issue Description: If the user clicks at a breadcrumb linking to one of the above mentioned screens (from newly created task on "Details of Task Queue" screen), he is redirected to the corresponding previous input screen, which still shows the notification area of the previously created payment and a series of error icons on all mandatory blocks. 3. Workaround: Reaccess the affected screens via menu structure. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Restricted user experience when using breadcrumb functionality. 6. Required SW change: Correct behaviour of breadcrumb functionality. | RTGS | 2025-06-14
PBI000000233050 |  | 1. Business Scenario Description: A party using a multi-addressee BIC is an entity authorised to submit and receive payment orders directly to/from RTGS and that does not hold an own RTGS DCA. This party must not necessarily belong to the same party as the account holder of the RTGS DCA. The user of an addressee BIC as the business sender of a cash transfer must be able to see the cash transfer in the List/Details of Cash Transfer(s) screen. 2. Issue Description: When a multi-addressee, which does not belong to the same party as the account holder, is the business sender of a cash transfer, the business sending user is not able to see the submitted cash transfer. 3. Workaround: not available for the view on the GUI, but instructions to modify any cash transfer orders can be sent A2A 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: When the user of an multi-addressee BIC cannot see the cash transfer in the List/Details of Cash Transfer screen, a change of the From/Till time via GUI is not possible as only the business sender of a cash transfer is allowed to change this. 6. Required SW change: Yes (Adapt further data scope checks for a GUI user regarding the business sender or receiver (From/To BIC BAH) in the implementation.) | RTGS | 2025-06-14
PBI000000233092 |  | 1. Business Scenario Description: A file which is parked due to close of service should be processed correctly when restarted. 2. Issue Description: A file send due the close of service (parked file) will not be processed. 3. Workaround: Do not send files in the close of service period. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: A parked file will not be processed. 6. Required SW change: Yes | RTGS | 2025-06-14
PBI000000233460 |  | 1. Business Scenario Description: The participant submitted a pacs.004 which was rejected with error E016 because the wrong business day was shown in GUI header. 2. Issue Description: Add the time were the pacs.004 entered the system, it was already in business day phase of 10000 of the next business Day 2024-06-20. But the GUI still showed the previous business day 2024-06-19. This led to the fact that the pacs.004 was rejected with E016 and it was not visible on the cash transfer query screen as well. 3. Workaround: Refresh GUI or log off / log on again in GUI 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: n/a 6. Required SW change: A check should be taken into account to inform the customer about the business day change via a pop up screen. | RTGS | 2025-06-14
PBI000000233495 |  | 1. Business Scenario Description: In case of pain.998 ASInitiationStatus for procedure D the settlement amount should be provided only for those cash transfers which have been executed partially. For AS transfers which have been fully settled no settlement amount is provided in the outbound message. 2. Issue Description: The settlement amount of a partial settled cash transfer was provided for all AS transfers and not only for the partially settled one. 3. Workaround: n/a 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: n/a 6. Required SW change: Adaption of current implementation. | RTGS | 2025-06-14
PBI000000233654 |  | 1. Business Scenario Description: Being logged in the GUI when T2 enters Close of Service. 2. Issue Description: The background check for broadcasts fails silently without displaying an error. 3. Workaround: n/a 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Customer does not receive information about the system being in close of service via the background checks. The error is only displayed via the "normal" error notification if the user manually triggers an action. 6. Required SW change: Yes, display information more prominent to the user when the API returns that the System in Close of Service. | RTGS | 2025-06-14
PBI000000233665 |  | 1. Business Scenario Description: Disagreeing a blocked AS batch on the RTGS GUI Screen 'List of AS Batches' and 'Details of Task Queue'. 2. Issue Description: When disagreeing on a blocked AS batch, the error Code U070 is raised unexpectedly in case a second user tries to confirm the corresponding task on the 'Details of Task Queue' screen. 3. Workaround: Let the batch sit as blocked until Eod is reached and the batch will be rejected automatically. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Disagreement of a blocked AS batch is not completely functional. 6. Required SW change: Yes, the task processing for the disagreement of AS batches has to be corrected. | RTGS | 2025-06-14
PBI000000233818 |  | 1. Business Scenario Description: Querying messages of the type "Return Business Day Information (camt.019)" via the GUI screen "Query Messages". 2. Issue Description: After selecting "Return Business Day Information (camt.019)" in the field "Message Type", no results are shown in the subsequent "List of Messages" screen. While this is correct for camt.019 messages which were sent as responses to a query, this behaviour is incorrect for camt.019 push notifications. This is only a GUI issue, the camt.019 message is correctly sent to the relevant party. 3. Workaround: No 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Camt.019 push notifications can not be displayed in the GUI. No processing issue. 6. Required SW change: Correct an implementation error which is preventing camt.019 push notifications from being able to be displayed (creation of an entry in a database table which is needed for the display in the GUI). | RTGS | 22/11/2025
PBI000000233938 |  | 1. Business Scenario Description: In case of the use of the guarantee funds mechanism and the guarantee funds account is blocked, with SDD-CN-126 the use of the guarantee funds mechanism should not be executed due to the blocked account. The AS batch as well as the related cash transfers in an intermediate status should be rejected with A085.. 2. Issue Description: The cash transfers are rejected with A084 instead of A085. But the batch is rejected as expected with SDD-CN-126. 3. Workaround: n/a 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: n/a 6. Required SW change: yes Applicable for user testing: yes | RTGS | 2025-06-14
PBI000000233995 |  | 1. Business Scenario Description: A query message must be sent via RT network. In case the SnF network is used the error code E002 is returned back (unknown namespace for the settlement service / network service). 2. Issue Description: The admi.007 which should return back the error code E002 can not be created due to a technical error. 3. Workaround: Do not send query messages via SnF network. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Query messages sent via SnF will not receive any response and business transaction will not automatically close 6. Required SW change: Yes | RTGS | 2025-06-14
PBI000000234028 |  | 1. Business Scenario Description: Using the Query BIC pop-up to select an Account BIC via smartselect input on GUI screens "Query Cash Transfers", "Query Account Postings", "Download Statement of Account", "Query RTGS Cash Account Liquidity", "Query Bilateral Limits", "Query Bilateral Limits", "Query AS Batch Liquidity Summary by Settlement Bank", "Query Linked AS Technical Accounts Procedure D", "Query Direct Debits". 2. Issue Description: When scrolling through the result list, the list remains visible above the table header. This issue can be tested by the customer and is not currency-related. 3. Workaround: n/a 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: No functional restriction. 6. Required SW change: Yes, fix transparency of elements. | RTGS | 2025-06-14
PBI000000234087 |  | 1. Business Scenario Description: The task queue displays the amount of the underlying cash transfers for the task type "Enter payments". 2. Issue Description: The amount for the task type "Enter Payment" with the attribute "pacs.004" displays the "Original Interbank Settlement Amount" instead of the "Returned Interbank Settlement Amount". It is only a visual bug and does not impede the processing of the task or cash transfer. 3. Workaround: The detailed information regarding the task is displayed in the divider "Overview Task" on the "Details of Task Queue" screen and there the "Returned Interbank Settlement Amount" is visible for the corresponding task. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: This bug could lead to confusion especially with regard to the 4-eyes principle and a possible control user. 6. Required SW change: Yes. The "Returned Interbank Settlement Amount" should be displayed in the amount field for the task type "Enter Payment" with the attribute "pacs.004". Applicable for user testing: yes | RTGS | 2025-06-14
PBI000000234095 |  | 1. Business Scenario Description: The E2E IDs and Instruction IDs for AS transfers should be displayed in the RTGS List/Details of Cash Transfer(s) screens. 2. Issue Description: For AS transfers stemming from the reversal of AS batches in Procedure A and B, resulting from the conversion of procedure B to A and resulting from invoke of the AS Guarantee Funds Mechanism, the E2E IDs and Instruction IDs are not shown in the RTGS List/Details of Cash Transfer(s) screens. 3. Workaround: n/a 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: n/a 6. Required SW change: Yes. The implementation must be adapted in order to display the E2E IDs/Instructions IDs for certain AS transfers. | RTGS | 2025-06-14
PBI000000234169 |  | 1. Business Scenario Description: When an ASTI pain.998 is sent to RTGS, several validation processes ensure a faultless processing of the AS batch. Amongst these validations it is checked that all BICs of the AS transfer initiation transactions are valid. In case the validation process identifies an invalid BIC, the linked AS transfer initiation transaction must be updated with the error code "D008" and gets the AS transfer status "INVL". This enables the customer to identify which AS transfer initiation transaction has been invalid. 2. Issue Description: The error code "D008" after the fix is now reported on AS transfer initiation transaction level and the AS batch gets the status ôINVLö correctly. However, all following transactions reported after the AS transfer initiation transaction with the wrong BIC in the pain.998 ASIS are also reported with the status ôINVLö and the error code ôD008ö. The faulty BIC cannot be easily identified by the customer as requested and the AS batches often contain a large number of transactions. This still causes inconvenience for the customer. 3. Workaround: n/a 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: not available 6. Required SW change: Code change to delete the restriction that if the ISO-D validation has failed for one AS transfer initiation transaction, no further validation is done anymore and all following AS transfer initiation transactions are reported as invalid containing the same error code. | RTGS | 2025-06-14
PBI000000234277 |  | 1. Business Scenario Description: Some attributes shown for outbound messages on the screen List of Messages are taken over from the corresponding inbound message (e.g. the original UETR). Irrespective of the number of inbound messages associated with an outbound message, the outbound message should always be shown on the screen only once. 2. Issue Description: There are cases where an outbound message is associated with at least two inbound messages (e.g. an outbound pain.998 with an inbound pain.998 and an inbound camt.025) and a value relevant for the display of the outbound message is not determined uniquely due to an implementation error. In this case the outbound message is shown several times. 3. Workaround: none 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: No consequences for the business processing, this is only a display issue. The effect materializes for a subset of outbound messages with more than one associated inbound message. The issue is relevant for all currencies and can be tested by customers (e.g. outbound pain.998 with an inbound pain.998 and an inbound camt.025). No SDD CN required. 6. Required SW change: ensure that every outbound message is shown only once, irrespective of the number of associated inbound messages. | RTGS | 2025-06-14
PBI000000234283 |  | 1. Business Scenario Description: When an AS batch of procedure C, D and E is fully processed and contains cash transfers with different final status, the AS batch gets the AS batch status ôACSCö and group status ôPARTö. 2. Issue Description: Due to a technical error, currently these AS batches get the AS group status ôACSCö instead of ôPARTö which is reported in the pain.998 ASIS global. Settlement is correct, AS batch status is correct and AS transfer initiation transactions are assigned the correct AS transfer status. Issue does not occur in case of pain.998 ASIS single for procedure E. 3. Workaround: n/a 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: n/a 6. Required SW change: Code change that AS batch group status is kept with value ôPARTö instead of update to ôACSCö. | RTGS | 22/11/2025
PBI000000234286 |  | 1. Business Scenario Description: Opening the "Overview Task" divider (buttons) are seen in the RTGS/CLM GUI screen "Details of Task Queue" for tasks of type "Enter Payment". 2. Issue Description: The buttons 'Collapse All' and 'Expand All' at the end of the "Overview Task" divider are not shown for all variants of the task type "Enter Payment" (e.g. pacs.008 in RTGS). The buttons should be available for all variants of the task type. This issue can be tested by the customer and is not currency-related. 3. Workaround: Use the individual collapsable sections by using the '+' icon. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: No 6. Required SW change: Yes, add the buttons to the GUI. | RTGS | 2025-06-14
PBI000000234291 |  | 1. Business Scenario Description: Using the field "AS Party BIC" on the RTGS GUI screens "Query AS Batches", "Query AS Procedures and Cycles" and "Query AS Batch Liquidity Summary by Settlement Bank". 2. Issue Description: In case the field is pre-filled and therefore in read-only mode (this occurs if the user only has access to one Party), the multi select fields dosen't show the content (at least the first element), but the number of the elements only (e.g. "All 1 items selected"). This issue can be tested by the customer and is not currency-related. 3. Workaround: N/A 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: No 6. Required SW change: Yes, show the content of the elements for read-only fields. | RTGS | 2025-06-14
PBI000000234302 |  | 1. Business Scenario Description: Edit a task of type "Change AS Settlement Period" 2. Issue Description: The original task is withdrawn and an error 400 occurs when trying to show the edit dialogue to the user. The task cannot be edited, but remains withdrawn. This issue can be tested by the customer and is not currency-related. 3. Workaround: Withdraw the task in question and enter a new task via the list of AS batches screen 4. TARGET Services concerned: T2 (RTGS) 5. Effects and restrictions on concerned TARGET Service: n/a 6. Required SW change: Yes, correctly load the AS batch in question for this task instead of the message. | RTGS | 2025-06-14
PBI000000234304 |  | 1. Business Scenario Description: A cash transfer query submitted with a InstructingAgent / InstructedAgent as search criteria should return cash transfers with these parameters as Creditor / Debitor corresponding cash transfers. 2. Issue Description: When the criteria InstructingAgent / InstructedAgent ('.../InstgAgt/...' or ''.../InstdAgt/...') are used, the camt.005 swaps them for every cash transfer except for pacs.010. 3. Workaround: Swap InstdAgt and InstgAgt in camt.005 (if not querying for pacs.010) when using 'PaymentIdentification' in the camt.005 message. Alternatively, use any other camt.005 search criteria apart from the 'PaymentIdentification'. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Cash Transfer Query returns wrong cash transfers. 6. Required SW change: Yes | RTGS | 22/11/2025
PBI000000234338 |  | 1. Business Scenario Description: Using the "Reset" button on the RTGS or CLM screen Details of Task Queue within the confirmation dialog of the following task types: pacs.008 "FI To FI Customer Credit Transfer" in RTGS, pacs.009 "Financial Institution Credit Transfer" in RTGS and CLM, pacs.004 "Payment Return" in RTGS 2. Issue Description: The "Reset" button also resets the currency of the "Interbank Settlement Amount" which is not visible to the user. Therefore the "Submit" button remains disabled even if all mandatory fields contain valid values. This issue can be tested by the customer and is not currency-related. 3. Workaround: Do not use the "Reset" button in the task queue confirmation dialog for the task types mentioned above. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: none 6. Required SW change: Yes, make sure the "Interbank Settlement Amount" currency will be set, if the related screens are used within the task queue. | RTGS | 2025-11-22
Problem ID*+ | Originating Service | Issue Description (BOD) | Impacted Module | Expected PROD Delivery Date
Production Problems Impacting Common Components (CoCo's)
PBI000000230211 | T2 | 1. Business Scenario Description: users trying to configure a new AAU for accounts linked to Contingency Accounts or trying to create new Contingency Accounts. 2. Issue Description: As stated in the ECONS II UDFS 1.3.2.5. Reference data for accounts in ECONS II û ôEach Authorised Account User can be linked to one and only one Contingency Accountö but on CRDM side no Business Rule prevents the creation of multiple Authorised Account Users with different AAU BICs for accounts which are linked to Contingency Accounts. 3. Workaround: no workaround available. Customers need to make sure that only one AAU is defined for accounts which are linked to Contingency accounts. 4. TARGET Services concerned: T2, T2S, TIPS 5. Effects and restrictions on concerned TARGET Service: no usage restriction. 6. Required SW change: During AAU creation, update and restore operations, CLM Accounts, System needs to check that CLM CB Accounts and Ancillary System Technical Accounts, if already linked to Contingency Accounts, cannot have multiple AAUs with different BICs for overlapping validity periods. During Contingency Accounts creation, update and restore operations, Linked Account needs to be checked to make sure that it has only one Authorised Account User during cash account validity period. 7. CRDM object:Authorised Account User, Cash Account | CRDM | 2025-06-14
PBI000000230942 | T2 | 1. Business Scenario Description: RTGS Directory is based on Authorised Account User and Cash Account configuration. To exclude a BIC from the directory, it should be referenceed in an AAU linked to a non published cash account or in an Exclusion participation type AAU, also within a wild card pattern. A BIC should be included only once within the same validity period in order to uniquely identify the correct addressing. 2. Issue Description: A BIC has been defined as Direct AAU on a non published account. The same BIC is included in a wild card pattern for a multi addressee AAU created on a published account. Expected behaviour should be that the BIC should not be part of the RTGS Directory. Currently the software wrongly includes the BIC when evaluating the wild card pattern instead of skipping it. The result is that a wrong record for the BIC is produced in the directory, causing as a side effect a double entry for the BIC with overlapping period. The fix aims at correcting the wild card pattern evaluation routine so that the processing is in line with the specs. 3. Workaround: In such scenario, if an additional AAU is created for the BIC on the published account with participation type set to "Exclusion", the record would not be included in the directory as expected. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: RTGS directory is used only in the context of RTGS and distributed to the RTGS participants, there is no impact on other services. 6. Required SW change: Yes. The wild card evaluation routine for the RTGS Directory extraction component should be corrected 7. CRDM object: RTGS Directory 8. DWH report: N/A | CRDM | 2025-06-14
PBI000000231653 | T2 | 1. Business Scenario Description: users trying to configure a new AAU for accounts linked to Contingency Accounts or trying to create new Contingency Accounts. 2. Issue Description: As stated in the ECONS II UDFS 1.3.2.5. Reference data for accounts in ECONS II û ôEach Authorised Account User can be linked to one and only one Contingency Accountö but on CRDM side no Business Rule prevents the creation of multiple Authorised Account Users with different AAU BICs for accounts which are linked to Contingency Accounts. 3. Workaround: no workaround available. Customers need to make sure that only one AAU is defined for accounts which are linked to Contingency accounts. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: no usage restriction. 6. Required SW change: During AAU creation, update and restore operations, CLM Accounts, System needs to check that CLM CB Accounts and Ancillary System Technical Accounts, if already linked to Contingency Accounts, cannot have multiple AAUs with different BICs for overlapping validity periods. During Contingency Accounts creation, update and restore operations, Linked Account needs to be checked to make sure that it has only one Authorised Account User during cash account validity period. 7. CRDM object: Authorised Account User, Cash Account | CRDM | 14/06/2025
PBI000000232168 | T2 | 1.Business Scenario: A duly authorized CRDM U2A user modifies the "System User Reference" field of a User falling under data scope. The modified user is employed by a party to access the ECONS2 module via U2A. 2. Issue Description: Due to a software bug, the user with a modified "System User Reference" cannot access the ECONS2 module via U2A until the next data propagation event. 3. Workaround: no workaround available. 4. TARGET Services concerned: ECONS2 5. Effects and restrictions on concerned TARGET Service: this only impacts the ECONS GUI. 6. Required software change: fix the software bug in order not to block the access to the ECONS GUI for the period between the modification of the "System User Reference" and the next data propagation. 7. CRDM object: User 8. DWH Report: N/A | CRDM | 2025-06-14
PBI000000232441 | T2 | 1. Business Scenario Description: RTGS directory is built from the Authorised Account User and includes BIC11 entries out of the possible wild cards defined for the AAUs. Deletion records should be included in the directory either if an AAU is closed for the upcoming business date and if a BIC is closed. 2. Issue Description: When a BIC is closed but there is a wildcard Authorised Account User including that BIC, a deletion record is not sent in the related directory. 3. Workaround: no workaround 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Directories on customer side out of date compared to actual active BICs. 6. Required SW change: The BIC Valid To date shall be considered when deletion records are processed 7. CRDM object: RTGS Directory, CLM Repository 8. DWH report: n/a | CRDM | 2025-06-14
PBI000000233623 | T2 | 1. Business Scenario Description: When performing a Liquidity Transfer Order update request in A2A, in case the Valid From is not specified in camt.024, the business rule DCU4073 is erroneously triggered. 2. Issue Description: Due to a software bug, Standing/Predefined LTO cannot be updated via A2A when Valid From field is not specified. 3. Workaround: Specify the Valid From field whenever updating the LTO via A2A or use the U2A channel to update the very same LTO. 4. TARGET Services concerned: T2, T2S. 5. Effects and restrictions on concerned TARGET Service: Standing/Predefined LTO cannot be updated via A2A when Valid From field is not specified. 6. Required SW change: Fix the software behavior of the business rule DCU4073 in order to handle the cases when the ôValid Fromö field is not specified in the input A2A request. 7. CRDM object: Liquidity Transfer Order. 8. DWH report: n/a | CRDM | 2025-06-14
PBI000000233350 | T2 | 1. Business Scenario Description: During a Data propagation Event, a properly configured party, is not correctly propagated to T2, the Party Code of the party is missing in the data propagation file. 2. Issue Description: The Party BIC Code is not correctly propagated to T2 if the Party-Party Code has been deleted. 3. Workaround: No workaround available 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: The propagation data doesn't include the Party BIC Code causing issue the the Data Propagation process. 6. Required SW change: The view needed to extract the Party Code take into consideration the last valid configuration of BIC Code of the Party and handles the Party codes deletion. 7. CRDM object: Data Propagation | CRDM | 2025-11-22
PBI000000233356 | T2 | 1. Business Scenario Description:A duly authorised CRDM U2A user attempts to create/update a CLM party-service link (PSL) defining the minor entity CLM configuration data. Specifically, it defines the the field "Maximum amount for overnight deposit" specifying a value comprising a decimal part (mantissa). 2. Issue Description: The problem depends on the fact that for the field "Maximum amount for overnight deposit", the decimal values are not currently handled by the CRDM GUI and BE side. Indeed, the correct behaviour is that the number decimal values of the "Maximum amount for overnight deposit" depends on the currency of the system entity. For example for the currency EUR there should be 2 decimals (cents). 3. Workaround: N/A 4. TARGET Services concerned: T2 (CLM) 5. Effects and restrictions on concerned TARGET Service: A user is not able to create/update a PSL defining the field "Maximum amount for overnight deposit" with the decimal part (mantissa) defined. 6. Required SW change: Add a new business rule to properly handle the correct field format the field "Maximum amount for overnight deposit", i.e., to check that it is compliant to the system entity currency. 7. CRDM object: Party-Service Link. 8. DWH report: N/A | CRDM | 2025-06-14
PBI000000234575 | T2 | 1. Business Scenario Description: A duly authorised CRDM User attempts to close a cash account referenced in a deleted Data Aggregation (e.g., Account Monitoring Group, Liquidity Transfer Group, Settlement Bank Account Group) causing the business rule DCU1030 to be wrongly triggered. 2. Issue Description: The current business rule check on the account linked in a Data Aggregation entity does not make a distinction between active and deleted groups. 3. Workaround: no workaround is feasible 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: if the cash account is referenced in a deleted data aggregation, it is not possible to close the account. 6. Required SW change: update of the processing of error DCU1030 in order to consider only the active data aggregation objects. 7. CRDM object: Data Aggregation (Account Monitoring Group, Liquidity Transfer Group, Settlement Bank Account Group) 8. DWH report: N/A | CRDM | 2025-11-22
PBI000000234545 | T2 | 1. Business Scenario Description:When the base Authorised Account User is closed, a deletion RTGS Directory record is included both in the full and update versions of the directory. 2. Issue Description: The deletion record for the scenario should be included in the directory produced for the Valid To + 1 business day. Currently it is included in the version valid for the Valid To date 3. Workaround: No workaround is available 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Customer application processing the directories could create wrong addressing for those records. 6. Required SW change: The RTGS DIrectory processing component needs to be fixed and consider the Valid To + 1 date when creating deletion records 7. CRDM object: RTGS Directory processing component 8. DWH report: | CRDM | 2025-06-14
PBI000000234605 | T2 | 1. Business Scenario Description: Wildcards authorised account users have been setup referencing the related RTGS Account. Some of the BICs included in the wildcard had been referenced in other Authorised Account User for a different TARGET Service. Those BICs have not been included in the RTGS Di-rectory. 2. Issue Description: Because of a failing algorithm, if the same BIC has been defined inside a wildcard for RTGS addressing and at the same time as authorised BIC for another TARGET Service (e.g. TIPS), the extraction of data resulted in the exclusion for these records. 3. Workaround: No Workaround available 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: A wrong RTGS directory content could lead to payment addressing issues for the partici-pants, reducing the reachability of impacted financial institutions. 6. Required SW change: Roll-back of the PBI causing the issue (hotfix), fixing of the data extraction logic in order to take account only authorised account users entry for the RTGS service. 7. CRDM object: - 8. DWH report: - | CRDM | 2025-11-22
PBI000000234566 | T2 | 1. Business Scenario Description: A duly authorised CRDM U2A user searches for liquidity transfer orders in the Standing/Predefined Liquidity Transfer Orders Search screen. Then, the very same user attempts to download the result list of the liquidity transfer orders. 2. Issue Description: when the "Amount From" specified in the search criteria of the mentioned screen is greater than 21,474,836, due to a software bug, it is not possible to download the result list of liquidity transfer orders. Some unexpected errors are raised in the GUI, namely, "Unable to Download Liquidity Transfer Orders" and "Unable to download Standing/Predefined Liquidity Transfer Orders". 3. Workaround: to download the very same set of objects, it is possible to remove the filter in the search criteria and apply it afterwards on the result list. 4. TARGET Services concerned: T2, T2S 5. Effects and restrictions on concerned TARGET Service: a CRDM U2A user is unable to export the liquidity transfer orders list. 6. Required SW change: fix the bug to allow users to export the liquidity transfer orders whenever any filter is applied on the "Amount From" field as a search criteria. 7. CRDM object: Liquidity Transfer Order 8. DWH report: N/A | CRDM | 2025-06-14
PBI000000234868 | T2 | 1. Business Scenario Description: During T2D2 data is provided by CRDM to T2 for data propaga-tion. Then with CCOS this data is prepared for the next business day. During data loading in T2D2 and T2PC multiple currencies are processed, where those currencies may have different next upcom-ing business days due to currency specific closing. Some object types from CRDM have a valid from and to date, which are compared with the next upcoming business day(s). 2. Issue Description: Data with such validity dates is not correctly identified per currency and the cor-responding next upcoming business day, which may lead to a loss of data provided by CRDM to T2. This deleted data is neither reported nor can be restored so any loss of data may not be identified. 3. Workaround: Make sure to have valid from before any closing or valid to after any closing. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Data provided by CRDM may be lost for the next business day without any notice. 6. Required SW change: Correctly consider next upcoming business day per currency. Remark: About 01.05.2025 the customer and CRDM should make sure, that valid data is available from before any closing or valid to after any closing. This can be monitored via Last Level Interven-tion. | CRDM | 2025-06-14
PBI000000232289 | T2 | 1. Business Scenario Description: Receiving A2A messages sent by the DWH 2. Issue Description: The field<DWHRptID> is useless in its current form and should be functionally converted to support the file splitting function 3. Workaround: None 4. TARGET Services concerned: T2-DWH 5. Effects and restrictions on concerned TARGET Service: The field is useless in its current form as it is not filled uniquely 6. Required SW change: Since the content of the field <DWHRptID> is deemed useless this field should contain a page number (in total in format '02/03" (meaning page 2 of 3)). This shall be applied together with the file split functionality which will make it possible, that also reports exceeding the 90MB file size limit can be sent via A2A as described in the DWH UDFS. In order for the receiver to know, how many pages he has to expect and in what order they need to be put together again, this information is indispensable. 7. CRDM object: - 8. DWH report: All | DWH | 2025-06-14
PBI000000232349 | T2 | 1. Business Scenario Description: Usage of T2-DWH PDR IDC03 2. Issue Description: Report can no longer display data that is prior to a CRDM change to the customer's account 3. Workaround: None 4. TARGET Services concerned: T2-DWH 5. Effects and restrictions on concerned TARGET Service: Changes to the customer's account can lead to new entries in a DWH table used by the report. As a result, only the most recent entry is listed as "Active". The report then uses the "Valid From" date of the "Active" entry as the earliest possible date to retrieve and display data. 6. Required SW change: Adjustment to the ETL process and the filtering of the report so that the report can also display entries without an "Active" flag 7. CRDM object: - 8. DWH report: IDC03 | DWH | 2025-11-22
PBI000000233529 | T2 | 1. Business Scenario Description: Usage of T2-DWH PDR IDH05 (Historical CRSS Data) 2. Issue Description: Some accounts are missing compared to previous CRSS reports 3. Workaround: None 4. TARGET Services concerned: T2-DWH (PROD only, as the CRSS data is only available there) 5. Effects and restrictions on concerned TARGET Service: Due to dependencies in the historical static data, it is possible that the objects have not been assigned to the corresponding data scope and therefore cannot be called up 6. Required SW change: Adjustment and extension of the historical static data, as well as a reload and/or adjustment of the corresponding data tables in order to be able to carry out a correct allocation 7. CRDM object: - 8. DWH report: IDH05 / CRSS Data Objects | DWH | 2025-06-14
PBI000000233848 | T2 | 1. Business Scenario Description: Usage of DWH Data Object "Parties - Cash Accounts - Other Info.Cash Accounts Private Data" in User Defined Report. 2. Issue Description: Missing columns regarding Co-Management and MR Inclusion in elements of data object. 3. Workaround: None 4. TARGET Services concerned: T2 DWH 5. Effects and restrictions on concerned TARGET Service: Usage of DWH data object is restricted due to missing data 6. Required SW change: The ETL job for the source table of "Cash Accounts Private Data" needs to be redesigned. After deployment of this change, a purge and a complete reload of this table is mandatory on all stages. 7. CRDM object: n.a. 8. DWH report: ANS01, IDC01, IDC02, IDC03, IDC04, IDC05 | DWH | 22/11/2025
PBI000000234015 | T2 | 1. Business Scenario Description: Usage of T2-DWH PDR PAR02 2. Issue Description: DWH Report PAR02 shows an excessive number of participants 3. Workaround: None 4. TARGET Services concerned: T2-DWH 5. Effects and restrictions on concerned TARGET Service: Due to an incorrect aggregation, the number of participants displayed in the report is too high. This exceeds the number of entries. 6. Required SW change: Adjustment of the counting function so that the number in the report matches the entries in the report and CRDM 7. CRDM object: - 8. DWH report: PAR02 | DWH | 2025-06-14
PBI000000234049 | T2 | 1. Business Scenario Description: Usage of T2-DWH & T2S-DWH PDR 2. Issue Description: The Tab Issue defines that only the first tab of the HTML version is exported when using Excel Data, CSV and XML 3. Workaround: Advanced users can schedule every tab as UDR in most cases 4. TARGET Services concerned: T2-DWH & T2S-DWH 5. Effects and restrictions on concerned TARGET Service: Some of the existing PDRs are divided into several tabs to make them easier for users to understand. These tabs are displayed correctly in formats that are optimized for U2A use (HTML, PDF and Excel). However, formats that are optimized for A2A processing (Excel Data, CSV and XML) are only exported with the first tab due to a COGNOS setting that cannot be changed. 6. Required SW change: Extension of the prompt page to include a query as to which page is intended for export in Excel Data, CSV and XML formats. This can also be used for scheduling. 7. CRDM object: - 8. DWH report: All DWH PDR with more than one tab T2: BDY01, BIL01*, BIL02, BIL03*, CON01, IDC02, MIR01, PAR01, PAR02, PAR03, TRN05, TRN07, TRN08. TRN09*, TRN10, TRN11* T2S: INX01, RAL01, SCT03 PDRs marked with * also contain the data issue (PBI000000234051), which must be considered separately | DWH | 22/11/2025
PBI000000234051 | T2 | 1. Business Scenario Description: Usage of T2-DWH & T2S-DWH PDR 2. Issue Description: The Data Issue defines that only the first list / report objects are reflected when using Excel Data, CSV and XML (in consequence not all data are displayed) 3. Workaround: Workaround via Excel (manual conversion into csv for example) 4. TARGET Services concerned: T2-DWH & T2S-DWH 5. Effects and restrictions on concerned TARGET Service: Some of the existing PDRs are divided into several tables to make them easier for users to understand. These tables are displayed correctly in formats that are optimized for U2A use (HTML, PDF and Excel). However, formats that are optimized for A2A processing (Excel Data, CSV and XML) are only exported with the first table due to the fact the machine-readable formats require a uniform table structure. 6. Required SW change: Output of the data as raw data without the respective formations in order to achieve a uniform table structure. 7. CRDM object: - 8. DWH report: All DWH PDR with more than one table T2: ANS02, BIL01*, BIL03*, INV01, TRN03, TRN04, TRN06, TRN09*, TRN11* T2S: RES01, RES02, SCT04, SST01, SST02, SST03 PDRs marked with * also contain the tab issue (PBI000000234049), which must be considered separately | DWH | 22/11/2025
PBI000000234411 | T2 | 1. Business Scenario Description: Usage of predefined report MIR01 2. Issue Description: No data found on tab 2 (interest rates) in case user selected one or more parties on the prompt page 3. Workaround: Do not use the party filter 4. TARGET Services concerned: T2 DWH 5. Effects and restrictions on concerned TARGET Service: The MIR01 report does not work as specified in the special case a party filter is used 6. Required SW change: For the MIR01 report the implementation of the party filter in Cognos has to be modified to use the DWH internal party technical identifier (Party_SK) instead of the Party_BIC. 7. CRDM object: - 8. DWH report: MIR01 | DWH | 2025-06-14
PBI000000234611 | T2 | 1. Business Scenario Description: Usage of T2-DWH PDR STA01 and STA02 2. Issue Description: If an entry in BIC Directory has been updated and therefore has got a new valid from date, no account postings from before this date are reported by STA01 and STA02 for accounts related to this BIC 3. Workaround: None 4. TARGET Services concerned: T2-DWH 5. Effects and restrictions on concerned TARGET Service: Due to an incorrect join between the account postings table and the BIC directory based on the account BIC (= AAU with participation type 'Direct') no postings from before the valid from date of the appropriate entry in the BIC directory for this account BIC are available. This is a Cognos error so that no reloading is necessary and the data is stored correctly in the database. 6. Required SW change: Adjustment of a join in the Cognos Framework Manager so that the validFrom dates of the BIC directory rows are not taken into account. 7. CRDM object: - 8. DWH report: STA01, STA02 | DWH | 2025-06-14
PBI000000234950 | T2 | 1. Business Scenario Description: Usage of T2-DWH PDR MIR01 2. Issue Description: Report MIR01 does not contain any parties that are no longer active 3. Workaround: None 4. TARGET Services concerned: T2-DWH 5. Effects and restrictions on concerned TARGET Service: Due to a faulty filter, only parties with the status Active are included in the report. As a result, parties that have been deleted are no longer visible in the report. 6. Required SW change: Adjustment / Removal of the filter, which only processes parties in the Active status. This is an adaptation of the ETL process. The fix only has an immediate effect on data that is processed after deployment with the corrected ETL. A correction of the historical data is necessary and should be carried out in a timely manner 7. CRDM object: - 8. DWH report: MIR01 | DWH | 2025-11-22
PBI000000234413 | T2 | 1. Business Scenario Description: BILL CoCo offers some A2A features such as: - camt.077 INVC: same data of PDF Invoice are reported in a ISO20020 message which is sent by the platform to properly configured participants. - A2A Query CUMU: it is possible for properly configured participants to query billable items of the invoice in cumulative way using a camt.076 CUMU request, the platform in turn sends back a camt.077 response containing requested data. 2. Issue Description: in camt.077 INVC and camt.077 CUMU there are some issues with tags containing description both for service item calculated by the system and by those added by the customer using manual corrections. In details: - in camt.077 INVC description of service items added using for manual corrections (Docu-ment/BllgRpt/BllgRptOrErr/BllgRpt/SvcCtgyTtls/SvcItmCrrctn/Desc) is missing; - in camt.077 CUMU description of service items calculated by the system (Docu-ment/BllgRpt/BllgRptOrErr/BllgRpt/SvcCtgyTtls/SvcItmTtls/Desc) is missing 3. Workaround: customer can find description of service items reported in camt.077 INVC and CUMU in PDF Invoice. 4. TARGET Services concerned: T2, TIPS, T2S 5. Effects and restrictions on concerned TARGET Service: description of service items add-ed by manual correction is missing in camt.077 INVC, description of service items calculated by the system is missing in camt.077 CUMU. 6. Required SW change: BILL CoCo A2A component must be fixed in order to properly popu-late description of service items added by manual correction in camt.077 INVC and descrip-tion of service items calculated in camt.077 CUMU. 7. CRDM object: na 8. DWH report: na | BILL | 2025-11-22
PBI000000234132 | T2S | 1. Business Scenario Description: CRDM User trying to create a Party. 2. Issue Description: when a CB User is trying to create a National Central Bank Party, the operation is rejected with an unknown technical error instead of a classic Business Rule. 3. Workaround: not present and not needed, this business case is not foreseen for customers. 4. TARGET Services concerned: T2, T2S, TIPS. 5. Effects and restrictions on concerned TARGET Service: no restrictions. 6. Required SW change: software fix in order to display the correct triggered Business Rule, instead of the technical error. 7. CRDM object: Party. 8. DWH report: n/a. | CRDM | 2025-06-14
PBI000000234166 | T2S | 1. Business Scenario Description: A user clicks on CMB details button of the Limit Search/List screen. 2. Issue Description: Due to an issue in the update of the CMB details button status of the Limit Search/List screen, when selecting a T2 multilateral limit the ôCMB detailsö button is wrongly enabled; additionally, after clicking on this button it is displayed the CMB details screen related to a limit different from the previous selected. 3. Workaround: No workaround. 4. TARGET Services concerned: T2, T2S, TIPS. 5. Effects and restrictions on concerned TARGET Service: No effects and restrictions since it is just a visualization issue. 6. Required SW change: The SW change will fix an issue in the update of the CMB details button status of the Limit Search/List screen. 7. CRDM object: Limit. 8. DWH report: N/A. | CRDM | 2025-06-14
PBI000000234204 | T2S | 1. Business Scenario Description: BILL user trying to print the .pdf file of the Itemised Invoice Data Details screen for download purposes, using the related on-screen button. 2. Issue Description: After hitting the button, the GUI does not produce any .pdf file. 3. Workaround: Exporting the screen content in .xls with the export button. 4. TARGET Services concerned: T2, T2S, TIPS. 5. Effects and restrictions on concerned TARGET Service: minor restriction on .pdf exporting. 6. Required SW change: GUI fix in order to correctly produce the .pdf file of the webpage after hitting the button. 7. CRDM object: n/a. 8. DWH report: n/a. | BILL | 2025-06-14
PBI000000234361 | T2S | 1. Business Scenario Description: CRDM User displaying the details of an existing Message Subscription Rule Set (and the whole set of its rules) via the dedicated Message Subscription Rule Set Details GUI screen. 2. Issue Description: Due to some wrong filtering conditions, the GUI is not able to display Message Subscription Rules having 0 predicates. 3. Workaround: no workaround feasible. 4. TARGET Services concerned: T2, T2S, TIPS. 5. Effects and restrictions on concerned TARGET Service: no restrictions since empty rules have no effects in the system. 6. Required SW change: CRDM GUI filtering fix in order to display all the rules, unconditionally. 7. CRDM object: Message Subscription Rule. 8. DWH report: n/a. | CRDM | 2025-06-14
PBI000000233438 | TIPS | 1. Business Scenario Description: The operating modules record the consumption made by the participants on the TARGET services, aggregate them on a daily basis by service item, party to be charged and responsible party and produce the Daily Aggregated Consumption Data. These are sent to BILL which enriches and validates them with CRDM configurations. Then BILL aggregates Daily Aggregated Consumption Data by the period to which the invoice will refer and by responsible party and then produces the Aggregated Consumption Data. Starting form Aggregated Consumption Data for a system entity, then BILL calculates the price to apply based on the configuration of Service Items and produces the Invoice Data. 2. Issue Description: Due to the absence of a valid price in a time interval for Service Item already configured in CRDM, BILL abends for an entire community/Service. The invoice data generetion process is stopped. In this case, new service items should have started to be included into invoices from July 2024 setting Valid From of them to 01/07/2024 in CRDM. But these new service items started to be included in the billing calculation in June 2024. Since their validity started from July, instead of skipping them (not valid in June), invoice data generation process was stuck. 3. Workaround: Configure Service Items with valid price for the relevant Billing Period 4. TARGET Services concerned: All Services are involved 5. Effects and restrictions on concerned TARGET Service: Billing process is stuck and no Invoice Data or PDf invoices are generated 6. Required SW change: A fix should be put in place to prevent BILL from going abend for an entire community/Service due to the absence of a valid price in a time interval for a service item already configured in CRDM. 7. CRDM object: 8. DWH report: | BILL | 2025-06-14
PBI000000233483 | TIPS | 1. Business Scenario Description: Into the Invoice, the invoice issuer can insert debit or credit items in addition to the ones relative to TARGET services consumption, this information is stored by Manual Correction entity. These additional items can refer to an already registered Service Item or to a custom one. It is possible to add Manual Correction also when the Participant has no consumption 2. Issue Description: In case the participant has no consumption, adds a Manual Correction and then deletes it, it is not possible to insert any other manual correction for the same participant, billing period and service. 3. Workaround: no workaround 4. TARGET Services concerned: all services are involved 5. Effects and restrictions on concerned TARGET Service: when the problem occurs it is not possible to insert any other manual correction for the same receiving party, billing period and service. 6. Required SW change: A software fix should be implemented to allow Manual correction to be inserted for a participant with no consumption and on which a Manual correctio has been already inserted and deleted. 7. CRDM object: na 8. DWH report: na | BILL | 2025-06-14
PBI000000233493 | TIPS | 1. Business Scenario Description: Before the creation of the invoices, the invoice data can be complemented with additional service items inserted as manual corrections for both CBs and CB Participants. In case a party did not perform consumption during the billing period, it is still possible to add manual correction, this result in the creation of an invoice dataset containing only the manual correction which will be reflected in the related invoice. 2. Issue Description: When a manual correction is added for a party without consumption BILL creates the related invoice data set, if the party BIC code is associated in CRDM also to other parties in different validity periods, BILL creates invoice dataset containing the same manual correction also for these parties despite the validity period of their BIC code. This results in multiple rows displayed in Invoice Data List screen for the same manual correction. 3. Workaround: The manual correction is correctly added so for the user performing the operation no workaround is needed. Instead an LLI is needed to ignore invoice dataset created for other parties. 4. TARGET Services concerned: TIPS, T2, T2S (Only CB users). Please note that the scenario is very uncommon considering its preconditions (BIC code used by different parties in different validity periods and manual correction added to a party without consumption). 5. Effects and restrictions on concerned TARGET Service: Multiple rows displayed in Invoice Data List screen for the same manual correction. 6. Required SW change: BILL must take into account the validity period of the party BIC in the creation of manual correction for a party without consumption avoiding multiple occurrences. 7. CRDM object: na 8. DWH report: na | BILL | 2025-06-14
PBI000000233501 | TIPS | 1. Business Scenario Description: A community (NCB + Participants) can perform consumption in different currencies (e.g. EUR and non-EUR currency). In CRDM configuration, this result in different system entityes having the same country code but different currencies. Consumptions performed by community must be processed properly by billing process both for EUR and non-EUR currency (via CR CSLD 0088 changes). 2. Issue Description: If a community perform consumption in different currencies (different system entities with same country code but different currencies), the billing process gets stuck for both system entities. 3. Workaround: LLI performed by 4CB, no workaround via application. 4. TARGET Services concerned: TIPS, T2, T2S 5. Effects and restrictions on concerned TARGET Service: Billing process gets stuck for both system entities in which community perform consumption. 6. Required SW change: BILL must be able to manage consumption of the same community in different currencies. 7. CRDM object: na 8. DWH report: na | BILL | 2025-06-14
PBI000000234035 | TIPS | 1. Business Scenario Description: As per the TIPS CR0066, It is requested that BILL is able to process and display unit prices with 5 decimals. This implies: (i) the possibility to capture the unit price in CRDM with at maximum 5 decimal positions (ii) the usage of the unit price (at maximum 5 decimal positions) in any relevant BILL automated process, BILL screens, and A2A/U2A invoices/queries. 2. Issue Description: The customer is trying to insert a Manual Correction setting a unit price with 5 decimal digit but on the screen the error ôUnit price is invalidö is displayed and it is not possible to insert the manual correction since the button Submit is not enabled. 3. Workaround: No workaround. 4. TARGET Services concerned: T2, T2S, ECMS. Since the usage of the unit price (at maximum 5 decimal positions) in any relevant BILL automated process, BILL screens, and A2A/U2A invoices/queries is foreseen and the Manual Correction can be added for any Target Service, all Services are involved 5. Effects and restrictions on concerned TARGET Service: It is not possible to insert Manual Correction with 5 decimal position, and in particular it is not possible to manage the ACH fee for band 4 with its unit price set at EUR 0.00015 6. Required SW change: a software fix should be put in place in order to allow the insertion of prices with 5 decimal position for the Manual Corrections 7. CRDM object: n/a 8. DWH report: n/a | BILL | 2025-06-14
PBI000000233525 | TIPS | 1. Business Scenario Description: Creation of Authorized Account User object using a BIC that is not existing in the BIC Directory 2. Issue Description: In the business rule DCC2003 "The BIC pattern, unless it contains a wildcard, must refer to an existing and active BIC", the check on the existence of the inserted BIC is not correctly executed in the software because it is only executed in case of inserted AAU Valid From greater than the current business date, instead of equal or greater than current business date. 3. Workaround: No workaround available. 4. TARGET Services concerned: TIPS and T2 5. Effects and restrictions on concerned TARGET Service: Under the described scenario and conditions (i.e. Creation of AAU object with Valid From equal to the current business date and referencing a BIC that is not existing in the BIC Directory), the AAU will be created but the inconsistent setup could not be used by the respective TARGET service since it will not be possible to complete the CRDM configuration and create the related æDN-BIC RoutingÆ object (i.e. the check on BIC existence in BIC Directory will be performed by business rule DRC8003). 6. Required SW change: A change in the software is needed to correctly perform the check for business rule DCC2003 also when the inserted AAU Valid From date is equal to the current business date 7. CRDM object: Authorized Account User | CRDM | 2025-11-22
Problem ID*+ | Originating Service | Issue Description (BOD) | Impacted Module | Expected PROD Delivery Date
Production Problems Impacting ECONS II
PBI000000233668 |  | 1. Business Scenario Description: pain.998 not visible on ECONS II GUI 2. Issue Description: ECONS II back end does not manage correctly a BIC/Account inserted in the pain.998 and not included in the relevant SBAG 3. Workaround: no one 4. TARGET Services concerned: only ECONS II 5. Effects and restrictions on concerned TARGET Service: no one 6. Required SW change: yes, software will be aligned to the UDFS in order to show the failed msg with error ECO0040 7. CRDM object: no 8. DWH report: no | ECONS II | 2025-11-22
PBI000000234432 |  | 1. Business Scenario Description: double settlement of ECONS II balances in CLM 2. Issue Description: During the ECONS II closing process CLM settle balances related to one currency but not acknowlege one camt.053 for a different currency. ECONS II went in status Locked therefore, OT reopen the session, for every currency, solved the issue and then restart the closing procedure. ECONS II sent out camt.053 for both currencies so, CLM settled everything resulting in a double settlement for the first currency already settled in the previous closure. 3. Workaround: No 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: At the reopening of the ECONS II session, customers will not be able to perform transaction(s) for currency(ies) already acknowledged by CLM meaning that, in case of need, the current session must be closed and another session have to be open. 6. Required SW change: Yes, since CLM is not able to rolled back the first settlement and/or it is not able to postpone/avoid the first settlement, for instance, linking it to the negatively acknowledged camt.053, the fix aims to avoid double settlement of ECONS II balances in CLM. In order to do so no camt.053 is sent for the already settled currency and any new settlement(s) is prevented for all the already acknowledged currencies. 7. CRDM object: n/a 8. DWH report: n/a | ECONS II | 2025-06-14
Problem ID*+ | Originating Service | Issue Description (BOD) | Impacted Module | Expected PROD Delivery Date
Production Problems Impacting Other
PBI000000229708 |  | On some CLM/RTGS GUI Screens, when the table allows only one Item to be selected a second selection might not clear the previous row marking which might lead to two rows being highlighted. This Fix aims at removing this condition in order to reliably display the highlight only for the currently selected row. | Other | 2025-06-14
PBI000000231794 |  | 1. Business Scenario Description: Sending a cash transfer order query (camt.005) which contain certain restrictions to query only cash transfers containing a certain character-time (tag 'FrDtTm') or amount (tag 'EQAmt') should result in a camt.006 response which only contains such cash transfers 2. Issue Description: Due to a technical issue the query processing fails when one of these tags is included and no answer is returend. 3. Workaround: Do not include the mentioned tags in the camt.005 query. Try to resend the query without given tags. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: see above 6. Required SW change: Yes | Other | 2025-06-14
PBI000000232101 |  | 1. Business Scenario Description: In the CLM/RTGS GUI, the user name is displayed next to the logo of the respective CB in the top right of the screen. 2. Issue Description: In case the displayed user name is particularly long, the user name and the CB logo overlap so that the user name appears to be cut off. 3. Workaround: No 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: The user name may not be clearly readable, leading to a restricted user experience. 6. Required SW change: Reposition header elements to allow the correct display of longer user names. | Other | 2025-06-14
PBI000000233052 |  | 1. Business Scenario Description: For the CLM/RTGS List of Cash Account Reference Data screen several data scope filters are applied depending of the user logged in. 2. Issue Description: For sub accounts erroneously the data scope filter for Co-Management is applied and data scope filter for cross-border sub accounts is not applied. For T2S/TIPS accounts erroneously the data scope filter for Banking Group is applied for a user acting as a leader of the banking group. 3. Workaround: not available 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Regarding the applied data scope filter for sub accounts there is no effect as co-management is restricted to CLM account holders and cannot be propagated for sub accounts. Regarding the missing data scope filter for cross-border sub accounts AS and CB users on behalf do not have access to cash account reference data of cross-border sub-accounts. data could be requested by OT, so this is a minor issue. Regarding the data scope filter for Banking Group applied, the leader of a Banking Group currently has access to T2S/TIPS cash account reference data of the members of this Banking Group(national and cross-border). 6. Required SW change: Yes (Data scope filters must be corrected in the implementation.) | Other | 2025-06-14
PBI000000234460 |  | 1. Business Scenario Description: Using the "List of Party Reference Data" screen in CLM or RTGS. 2. Issue Description: The table columns "Exceptional Customer Credit Transfer Payments (pacs.008) Allowed" and "Exceptional Financial Institution Credit Transfer Payments (pacs.009) Allowed" are possibly not shown on the screen. If the results only contain the service party type "RTGS CB Account Holder" but not "RTGS Account Holder". The visbility of the related activate/deactivate context menu items is not affected. This issue can be tested by the customer and is not currency-related. 3. Workaround: n/a 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: none 6. Required SW change: Yes, make sure the service party type "RTGS CB Account Holder" is also taken into account while filtering the table columns to be displayed. | Other | 2025-11-22
PBI000000234621 |  | 1. Business Scenario Description: The screens "Details of Bilateral Limit" and "Details of Multilateral Limit" show the amount-fields "Queued Credits" and "Queued Debits". 2. Issue Description: The amount-fields "Queued Credits" and "Queued Debits" should show the respective amounts but are currently empty. 3. Workaround: Compute the sum of amounts of the respective list entries manually. 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: The amount fields are empty whenever the respective screen is opened. This can be tested by anay GUI user and is relevant for every currency. 6. Required SW change: The function displaying the respective amounts has to be fixed. | Other | 2025-06-14
PBI000000234622 |  | 1. Business Scenario Description: When executing any query function within the T2 GUI, returning a result list with a column containing an empty value. 2. Issue Description: When sorting the result list based on a column, which may contain empty cells, the empty cells are displayed differently depending on their technical variation of empty: Empty text is sorted as smallest value while null is always displayed at the end. This issue can be tested by the customer (by checking that empty columns are always sorted uniformly at the beginning/end of the result list). The issue is not currency-related. 3. Workaround: n/a 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: n/a 6. Required SW change: Yes, the sort of lists has to be adjusted to correctly display null values. | Other | 2025-11-22
PBI000000234267 |  | 1. Business Scenario Description: Using the "Date and Time Picker", the "Date Picker" or the "Time Picker" within the T2 GUI which are opened by clicking into an input field or clicking on the calendar/clock button next to an input field. 2. Issue Description: "Date and Time Picker", the "Date Picker" and the "Time Picker" have to receive a new layout due to an update of underlying technical implementation. The issue can be tested by the customer and is not currency-related.á 3. Workaround: none 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: Mostly visual changes, the functionality remains largely unchanged. Further details regarding the changes are described via SDD CN.áá 6. Required SW change: Yes, update to a new variant of the "Date and Time Picker", the "Date Picker" and the "Time Picker". SDD impact: Yes | Other | 2025-11-22
PBI000000234268 |  | 1. Business Scenario Description: After the successful settlement of a payment order CLM/RTGS should check whether it s necessary to create a floor/ceiling notification or liquidity transfer on both the credit and debit cash account of the payment. 2. Issue Description: In case the credit and the debit cash accounts have both either a floor/ceiling notification or liquidity transfer configured, the floor/ceiling check is not executed on both cash accounts but only on one of the two cash accounts. This issue can be tested by the customer and is not currency-related. 3. Workaround: - 4. TARGET Services concerned: T2 5. Effects and restrictions on concerned TARGET Service: It s possible that a configured floor/ceiling notification or liquidity transfer is not executed as expected after the settlement of a payment. 6. Required SW change: Adjusting the loop to select the correct account even on multiple runs through the loop. | Other | 2025-11-22